## Overview
ASELA Open Transport Data Initiative
Project Timeline
Version 2 | 2019-02-06

## Timeline
Project Phase | Activity | Who | time axis 2019-02-08 to 2020-03-30
Bid assessment | Application submission deadline | DfT | bar: 2019-02-08
| Applications assessed | DfT | bar: 2019-02-11 to 2019-02-15; 2019-02-18 to 2019-02-22; 2019-02-25 to 2019-02-28
| Successful applications identified and approved | DfT | bar: 2019-03-01; 2019-03-04 to 2019-03-05
| Contractual documents put in place | DfT and SBC | bar: 2019-03-06 to 2019-03-07
Mobilisation | Project commencement | SBC | bar: 2019-03-08
| Develop work specification | SBC | bar: 2019-03-11 to 2019-03-15
| Issue Invitation to Tender (ITT) | SBC | bar: 2019-03-18
| ITT received | SBC | bar: 2019-04-05
| Evaluate tenders | SBC | bar: 2019-04-08 to 2019-04-11
| Tender award | SBC | bar: 2019-04-12
| Issue purchase order for Siemens Stratos implementation | SBC | bar: 2019-04-12
Discovery | Mobilise delivery team | Sub contractor | bar: 2019-04-15 to 2019-04-18
| Meeting with client | Sub contractor / SBC | bar: 2019-04-23
| Identification of users | Sub contractor | bar: 2019-04-24 to 2019-04-26; 2019-04-29 to 2019-04-30
| Understand user requirements | Sub contractor | bar: 2019-05-01 to 2019-05-03; 2019-05-07 to 2019-05-10
| Identification of data feeds to open | Sub contractor / SBC / ASLEA | bar: 2019-05-13 to 2019-05-17
| Make contact with data owners | Sub contractor | bar: 2019-05-20 to 2019-05-23
| Understand data contents and ability to share | Sub contractor | bar: 2019-05-24; 2019-05-28 to 2019-05-31
| Understand data security and privacy arrangements | Sub contractor | bar: 2019-06-03 to 2019-06-07
| Agree data feeds feasible to open | Sub contractor / SBC / ASLEA | bar: 2019-06-10 to 2019-06-14
| Agree data security and privacy arrangements | Sub contractor / SBC / ASLEA | bar: 2019-06-10 to 2019-06-14
Implementation | Arrange agreements to share data | Sub contractor / SBC / ASLEA | bar: 2019-06-17 to 2019-06-21; 2019-06-24 to 2019-06-28
| Build data security and privacy arrangements | Sub contractor | bar: 2019-07-01 to 2019-07-05
| Build data connections | Sub contractor | bar: 2019-07-08 to 2019-07-12; 2019-07-15 to 2019-07-19
| Test data connections | Sub contractor | bar: 2019-07-22 to 2019-07-26
| Connect data feeds into existing data dashboard | Sub contractor | bar: 2019-07-29 to 2019-08-02
| Test data dashboard | Sub contractor | bar: 2019-08-05 to 2019-08-09
| User acceptance testing (UAT) | Sub contractor | bar: 2019-08-12 to 2019-08-16; 2019-08-19 to 2019-08-23
| Revisions following UAT | Sub contractor | bar: 2019-08-27 to 2019-08-30
| Make data feeds open | Sub contractor | bar: 2019-09-02
| Development of Stratos feeds | Siemens | bar: 2019-03-01; 2019-03-04 to 2019-03-08; 2019-03-11 to 2019-03-15; 2019-03-18 to 2019-03-22; 2019-03-25 to 2019-03-29; 2019-04-01 to 2019-04-05; 2019-04-08 to 2019-04-12; 2019-04-15 to 2019-04-18; 2019-04-23 to 2019-04-26; 2019-04-29 to 2019-05-03; 2019-05-07 to 2019-05-10; 2019-05-13 to 2019-05-17; 2019-05-20 to 2019-05-24; 2019-05-28 to 2019-05-31
Delivery | Stratos feeds live | Siemens | bar: 2019-06-03
| Make data dashboard available to users | Sub contractor | bar: 2019-09-02
| User training of data feeds and dashboard | Sub contractor / SBC / ASLEA | bar: 2019-09-03 to 2019-09-06; 2019-09-09 to 2019-09-11
| Receive user feedback | SBC / ASLEA | bar: 2019-09-12 to 2019-09-13; 2019-09-16 to 2019-09-17
| Make amendments to data feeds and dashboard | Sub contractor | bar: 2019-09-18 to 2019-09-20; 2019-09-23 to 2019-09-25
| Achieve steady state | Sub contractor / SBC / ASLEA | bar: 2019-09-26
Evaluation | Understand data points to measure | Sub contractor / SBC / ASLEA | bar: 2019-07-08 to 2019-07-12; 2019-09-27
| Agree data points to measure | Sub contractor / SBC / ASLEA | bar: 2019-07-15 to 2019-07-19; 2019-07-22 to 2019-07-26
| Take baseline measurements | Sub contractor / SBC / ASLEA | bar: 2019-07-29 to 2019-08-02; 2019-08-05 to 2019-08-09; 2019-08-12 to 2019-08-16; 2019-08-19 to 2019-08-23; 2019-08-27 to 2019-08-30
| Take progress measurements | Sub contractor / SBC / ASLEA | bar: 2019-09-02 to 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-20; 2019-09-23 to 2019-09-27; 2019-09-30 to 2019-10-04; 2019-10-07 to 2019-10-11; 2019-10-14 to 2019-10-18; 2019-10-21 to 2019-10-25; 2019-10-28 to 2019-11-01; 2019-11-04 to 2019-11-08; 2019-11-11 to 2019-11-15; 2019-11-18 to 2019-11-22; 2019-11-25 to 2019-11-29
| Evaluate measurements | Sub contractor | bar: 2019-12-02 to 2019-12-06; 2019-12-09 to 2019-12-13; 2019-12-16 to 2019-12-20; 2019-12-23 to 2019-12-24
| Develop project report | Sub contractor | bar: 2020-01-02 to 2020-01-03; 2020-01-06 to 2020-01-10; 2020-01-13 to 2020-01-17; 2020-01-20 to 2020-01-24
| Review project report | SBC / ASLEA | bar: 2020-01-27 to 2020-01-31; 2020-02-03 to 2020-02-07
| Finalise project report | Sub contractor | bar: 2020-02-10 to 2020-02-14
| Last day to spend project funds | SBC | bar: 2020-03-30